## Sheet1
Product : HRMS |  | Date: 4/04/2024
Module : Employee Details
Test By : Mohammed Sohail
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
DID_001 | Broken Image Displayed After Upload | Broken image displayed after successful upload | After successfully uploading an image while adding a new employee in the HRMS system, the displayed image appears broken or does not render properly. | 1. Log in to the HRMS system. 2. Navigate to the dashboard. 3. Click on the "Add New Employees" button. 4. Click on the "Add Employee" module. 5. Click on the "Add Employee" module button. 6. Upload an image. 7. Observe the displayed image. | Medium | High | Open | HRMS | https://ibb.co/WWcp96T | This issue affects the user experience as the displayed image is broken or does not render properly after successful upload. | Mohammed Sohail
DID_002 | Next Button Not Functional | Next button does not proceed to the next step | After filling in all required fields and clicking on the "Next" button while adding a new employee in the HRMS system, the button does not function as expected and does not proceed to the next step. | 1. Log in to the HRMS system. 2. Navigate to the dashboard. 3. Click on the "Add New Employees" button. 4. Click on the "Add Employee" module. 5. Click on the "Add Employee" module button. 6. Fill in all required fields. 7. Click on the "Next" button. | High | High | Open | HRMS | https://ibb.co/nCxz1gy | This issue prevents users from proceeding to the next step in adding a new employee, impacting workflow and data entry. | Mohammed Sohail